## Sheet1
GANTT CHART
Task Number | Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 & Week 8
|  | June 18- June 24 | June 24- July 1 | July 2- July 8 | July 9- July 15 | July 16- July 22 | July 23- July 29 | July 30 - August 12
1 | Gathering remaining required materials | bar: Week 1
2 | Finding subtitutes for non acquired materials | bar: Week 2
3 | Half sewing of soft & conductive fabrics to develop basic sensor | bar: Week 3
4 | Making the sensor region highly sensitive | bar: Week 4
5 | Developing to fully sewed stretchable sensor from soft sensor | bar: Week 5
6 | Pilot run with the e textile sensor | bar: Week 6
7 | Finalization and tests